## in
ID | Inspection Date(Report) | System Designation(Asset) | Asset Name | Route(Asset) | Feature Crossed(Asset) | District(Report) | Maintenance Section(Asset) | CF Critical Finding(Report) | Previously Recommended(Report) | Recommendation Type(Report) | Description of Issue(Report) | Workflow Stage | Assigned To | Bridge Owner(Report) | Area Office(Report) | Bridge Component(Report) | Repair Category(Report) | District Bridge Comments(Report) | Most Recent Workflow Comment
739959 | 2024-04-26 | 1 | 90140001504581 | IH 35 SBFR | LITTLE ELM CREEK | WAC | 1 | N | N | Level 3 | MBIT's Inspection Missing delineation along the bridge rail and MBGF. Recommendation: Install delineation to standard. | Area Office Review | Yates, Michael | TxDOT | Belton | Approaches | Provide Standard Delineation/Object Markers at Structure |  | Created FUA from MBITs inspection.
731846 | 2024-04-26 | 1 | 90140001504582 | IH 35 NBFR | LITTLE ELM CREEK | WAC | 1 | N | N | Level 3 | MBIT's Inspection Missing delineation though out. Recommendation: Install current standard delineation. | Area Office Review | Yates, Michael | TxDOT | Belton | Approaches | Provide Standard Delineation/Object Markers at Structure |  | Created FUA from MBITs inspection.
740000 | 2024-04-26 | 1 | 90140001504584 | IH 35 NBML | BERGER/HART RD | WAC | 1 | N | N | Level 3 | MBIT's Inspection Missing delineation. Recommendation: Install standard delineation throughout bridge rail. | Area Office Review | Yates, Michael | TxDOT | Belton | Deck | Provide Standard Delineation/Object Markers at Structure |  | Created FUA from MBITs inspection.
634524 | 2023-01-11 | 1 | 90140001504584 | IH 35 NBML | BERGER/HART RD | WAC | 1 | N | N | Level 3 | Minor to moderate deterioration of relief joint seals with some tears. RECOMMENDATION: Clean and reseal relief joints. | Area Office Review | Kasberg, Stephen | TxDOT | Belton | Approaches | Clean and Seal Relief Joints (Pavement/Approach Slab)
740676 | 2024-05-22 | 1 | 90140001514207 | IH 35 SBFR | NOLAN CREEK | WAC | 1 | N | N | Level 3 | MBIT's Inspection Channel is full of debris due to current weather. Recommendation: Remove debris in the channel. | Area Office Review | Yates, Michael | TxDOT | Belton | Channel | Remove Drift and Debris |  | Created FUA from MBITs inspection
742529 | 2024-06-05 | 1 | 90140001514335 | IH 35 SBFR | LEON RIVER | WAC | 1 | N | N | Level 3 | MBIT's Inspection Vegetation overgrown on SW side. Recommendation: Cut down the overgrown trees that are growing over and into the bridge rail. | Area Office Review | Yates, Michael | TxDOT | Belton | Channel | Trim Trees, Brush and Vegetation |  | Created FUA from MBITs inspection.
742526 | 2024-06-05 | 1 | 90140001514335 | IH 35 SBFR | LEON RIVER | WAC | 1 | N | N | Level 3 | MBIT's Inspection Missing object markers on rail. Recommendation: Install delineation to current standards. | Area Office Review | Yates, Michael | TxDOT | Belton | Deck | Provide Standard Delineation/Object Markers at Structure |  | Created FUA from MBITs inspection.
742535 | 2024-06-05 | 1 | 90140001514336 | IH 35 SBML | LEON RIVER | WAC | 1 | N | N | Level 3 | MBIT's Inspection Vegetation overgrown. Recommendation: Cut down overgrown trees that are growing into the bridge rails. | Area Office Review | Yates, Michael | TxDOT | Belton | Channel | Trim Trees, Brush and Vegetation |  | Created FUA from MBITs inspection.
742533 | 2024-06-05 | 1 | 90140001514336 | IH 35 SBML | LEON RIVER | WAC | 1 | N | N | Level 3 | MBIT's Inspection North abutment seal seems compromised. Recommendation: Install a new seal for the joint. | Area Office Review | Yates, Michael | TxDOT | Belton | Deck | Repair Joint |  | Created FUA from MBITs inspection.
742532 | 2024-06-06 | 1 | 90140001514336 | IH 35 SBML | LEON RIVER | WAC | 1 | N | N | Level 3 | MBIT's Inspection Missing object markers on rail. Recommendation: Install delineation to current standards. | Area Office Review | Yates, Michael | TxDOT | Belton | Deck | Provide Standard Delineation/Object Markers at Structure |  | Created FUA from MBITs inspection.
742546 | 2024-06-05 | 1 | 90140001514337 | IH 35 NBFR | LEON RIVER | WAC | 1 | N | N | Level 3 | MBIT's Inspection Bent 4 needs cleaning. Recommendation: Clean debris on top of bent caps. | Area Office Review | Yates, Michael | TxDOT | Belton | Substructure | Clean Debris from Top of Caps and Around Bearings |  | Created FUA from MBITs inspection.